## Approved Project - O&G Estimate
Great Oak Middle Schoool Evaluation & Improvements (TA: OXF02AR)
Project Tracking
Summary of Project Costs as approved by BOS, BOF & Town Meeting - 8/14/2019
- Up to $1,000,000 to be bonded and $409,226 to be funded from Capital Non-Recurring
- Work to be Completed by August beginning 2020-2021 School Tear
| Total Gross Area: | 73000 sf | Tecton Cost Estimate |  | O&G Estimates (See Sheet2)
Scope of Work |  |  | LS | Subtotal | Cost Estimate | Var -TT-OG
1.00 General Conditions |  |  |  |  | 164534 | -164534
1.01 Asbestos Abatement |  |  | 300000 | 300000 | 150000 | 150000
1.02 One-to-One Millwork Replacement |  |  |  | 104400 | 394950 | -290550
1.03 Select Ceiling Tile Replacement |  |  | 50000 | 50000 | 5000 | 45000
1.04 Wayfinding / Signage Throughout |  |  | 50000 | 50000 | 27886 | 22114
1.05 Furniture Replacement |  |  |  | 40000 | 20000 | 20000
1.06 Art Room Improvements |  |  |  | 38000 | 0 | 38000
Provide Built-In Perimeter Shelving w/Sink |  |  | 18000
Furniture Improvements |  |  | 20000
1.07 Gymnasium Improvements |  |  |  | 75000 | 113370 | -38370
Raised Platform w/Accessibility (24' X 40') |  |  | 32000
Room Divider Curtain |  |  | 15000
A/V Infrastructure (Relocate Existing Equipment, Provide Power) |  |  | 8000
Acoustic Wall Panels |  |  | 20000
1.08 Literacy Center Furniture Improvement |  |  | 20000 | 20000 | 23221 | -3221
1.10 Media Center |  |  |  | 28000 | 0 | 28000
Demolition of Temporary Partitions (2) |  |  | 8000
Furniture Improvements |  |  | 20000
1.09 Personalized Learning Center |  |  |  | 4000 | 0 | 4000
Demolition of Temporary Partition |  |  | 4000
1.15 Exterior Improvements |  |  |  | 323000 | 257500 | 65500
Site Prep & Playground |  |  | 150000
Exterior Paint, Caulk, Trim |  |  | 7500
Paving & Restriping of Parking Lot |  |  | 100000
Total |  |  |  | 1032400 | 1156461 | -124061 | 0 | 0
Professional Fees |  |  |  | 77430 |  | 77430 | Contingency to be Allocated to ChangeOrders
Design Contingency |  |  |  | 103240 |  | 103240 | Contingency to be Allocated to ChangeOrders
Escalation |  |  |  | 25810 |  | 25810 | Contingency to be Allocated to ChangeOrders
Liability Insurance (Builders Risk) |  |  |  | 15486 |  | 15486 | Contingency to be Allocated to ChangeOrders
Contractor Overhead & Profit |  |  |  | 103240 |  | 103240 | Contingency to be Allocated to ChangeOrders
Building Permit |  |  |  | 0 |  | 0 | Contingency to be Allocated to ChangeOrders
Owner's Contingency |  |  |  | 51620 |  | 51620 | Contingency to be Allocated to ChangeOrders
|  |  |  | 376826 |  | 376826
Total Project Cost AS APPROVED/Contingency Balance |  |  |  | 1409226 | 1156461
[6 empty] | 1409226 |  | 252765

## O&G Itemized
Itemized Project Components - Awarded Bids
Description |  | Amount | Sub-Total | Winning Bid | Varance | Status | Due Date | Bidder | Bid $ | Bidder | Bid $ | Bidder | Bid $ | Bidder | Bid $ | Bidder | Bid $
1.00 General Conditions
| Meyers Movers | 0 |  | 12306 |  | 12306 | Billed to Date |  | 0 | Varance
| USA Dumpsters | 0 |  | 8291.6 |  | Actual Billing - See Misc. Page for Invoice # Detail
| Tecton RFP Support | 0 |  | 2640
| Walshs Country Store |  |  | 1900 |  | Shed Move
| Asbestos Mitigation/Air Qual/Flooring | 164534
| **Total** |  | 164534 | 25137.6 | 139396.4
1.01 Asbestos Abatement
| Asbestos Mitigation | 150000 |  | 0 |  | GR
| Air Quality Testing |  |  |  |  | GR
| New Flooring |  |  |  |  | GR
| **Total** |  | 150000 | 0 | 150000
1.02 One-to-One Millwork Replacement | [5 empty] | OPS2020-04 | 2020-03-27
| Demo Base Cabinets (29 Areas) L22' x29' Ea) | 9528 |  |  |  | OPS2020-04
| Demo Upper Cabinets (29 Areas) L22' x29' Ea) | 9528 |  |  |  | OPS2020-04
| Wood Base Cabinets | 129514 |  |  |  | OPS2020-04
| Media CenterFurniture Improvments | 20000
| Wood Wall Cabinets | 123134 |  |  |  | OPS2020-04
| Countertops - Formica | 80974 |  | 378413 |  | OPS2020-04 |  | Legacy GC BID | 378413
1.06 Art Room Improvements | [5 empty] | OPS2020-04 | 2020-03-27 | Approved 5/6 BOS
| Demo Base Cabinets | 3870 |  |  |  | OPS2020-04
| Demo Upper Cabinets | 3650 |  |  |  | OPS2020-04
| Cabinet - Base Level Plam - Base Cabinet W/Sink | 960 |  |  |  | OPS2020-04
| Cabinet - Base Level Plam - Wall Cabinet | 1000 |  |  |  | OPS2020-04
| Countertops - Formica w/Wood Edge | 2792 |  |  |  | OPS2020-04
| Furniture Improvements (AIA Allow) | 2000 |  |  |  | OPS2020-04
| 3 New Sinks + U/G Drain to Bathroom | 5000 |  |  |  | OPS2020-04
| Cut & Patch Floor for Drain Line | 3000 |  |  |  | OPS2020-05 | 2020-04-10
| **Total** |  | 394950 | 378413 | 16537
1.03 Select Ceiling Tile Replacement
| Remove Ceiling Tile and Grid | 0 |  |  |  | Requirements
| Ceiling Plain Tile | 5000 |  |  |  | Requirements
| **Total** |  | 5000 | 0 | 5000
1.04 Wayfinding / Signage Throughout | [5 empty] | Requirements
| Remove Wayfinding Signs | 5161 |  |  |  | Requirements
| Remove Room Signs | 5075 |  |  |  | Requirements
| Sign - Room Id | 11320 |  |  |  | Requirements
| Sign - Exit | 6330 |  |  |  | Requirements
| **Total** |  | 27886 | 0 | 27886
1.05 Furniture Replacement
| Art Room & Personalized Learning Center | 20000 |  |  |  | Requirements
| **Total** |  | 20000 | 0 | 20000 | Requirements
1.07 Gymnasium Improvements
| Refurbish Existing Gym Divider | 27210 |  |  |  | Requirements
| Acoustical Wall Panels 8' High @ 2 Long Walls | 20160 |  |  |  | Requirements
| Raised Portable Platform W/Accessibility PO26432 | 58000 |  | 63800 |  | OPS2020-02 | 2020-03-05 | StageRight | 63800 | SICO | 69,000 24" no ramp or stage surround
Delete Gym Divider Curtain (Refurbish Existing)
| A/V Infrastructure(Relocate Existing Equipment, Power) | 8000 |  |  |  | Requirements | 2020-04-10
| **Total** |  | 113370 | 63800 | 49570 |  |  | Invoice #272388 Approved 8/26/2020 $63,800
1.08 Literacy Center Furniture Improvement
| Furniture Improvements | 20000 |  |  |  | Requirements
| Demo Wall & Rebuild |  |  |  |  | OPS2020-05 | 2020-04-10
1.09 Personalized Learning Center
| Demo Temp Partician L22' x H' | 741 |  |  |  | OPS2020-05 | 2020-04-10
| Paint & Touchup (estim) | 500 |  |  |  | OPS2020-05 | 2020-04-10
1.10 Media Center
| Demo Temp Partician (2Walls) L22 x H9' @ 2 Ea | 1480 |  |  |  | OPS2020-05 | 2020-04-10
| Paint Touch-Up (estimate) | 500 |  |  |  | OPS2020-05 | 2020-04-10
1.11 Ref #12 Demo & Rebuild 2 Walls | [5 empty] | OPS2020-05 | 2020-04-10
1.12 Ref #19-20 Demo 3 Walls, Rebuild 2 Walls | [5 empty] | OPS2020-05 | 2020-04-10
1.13 Ref # 24 - Demo 2 Walls & Rebuild 2 Walls | [5 empty] | OPS2020-05 | 2020-04-10
1.14 Ref # L4-L5 New Music Room - Demo 1 Wall |  |  |  | 149816 |  |  |  | Catalyst | 149816 | 5-7-2020 Including GYM & Bus Canopy
| **Total** |  | 23221 | 149816 | -126595 |  |  | Tabled 5/6
1.15 Exterior Improvements
| Exterior Building, Exterior Paint, Caulk & Paint | 7500 |  |  |  | OPS2020-05 | 2020-04-10
| Site Prep & Playground (rear of Building | 150000 |  | 74862 |  | OPS2020-06 | 2020-04-10 | Premier | 74862
| Pave & Restripe Parking Lot (Front of Building) | 100000 |  | 306700 |  | OPS2020-07 | 2020-04-10 | Marini | 302900 | S&S | 306700 | Guarrarra | 354000 | All American | 371210 | earthworks | 396228
| **Total** |  | 257500 | 381562 | -124062 |  |  | S&S Awarded |  | Awarded 3/6
| Project Financial Status (Budgeted/Awarded) | 1156461 | 1156461 | 998728.6 | 157732.4
Project Summary - Approved Versus Actual
Description |  | Approved |  | Actual
| Total Authorized/Total Awarded & Committed | 1032400 |  | 998728.6
| Professional Fees | 77430
| Design Contingency | 103240
| Escalation | 25810
| Liabability Insuarnce | 15486
| Contractor Overhead & Profit | 103240
| Buiding Permit | 0
| Owner"s Contingency | 51620
| Total Approved Change Orders |  |  | 344825.77
| Total Awarded Including Change Orders |  |  | 1343554.37
| Contingency - Approved/Remaining | 376826 |  | 65671.63
| Total Project - Approved/Actual | 1409226 |  | 1409226

## Change Orders
Change Orders
Description | Approved |  | Catalyst GenCon | Legacy Millwork | Saracco MEP | Bestec Asbestos | Misc BB,HVS,RK | Tecton & B&B Engineering | S&S Paving | Other
COVID-19 Insident - Clean Building | 2020-09-23 | 12000 |  |  |  |  | 12000
Legacy
CO#1 Replace Shutoff Valves | 2020-06-10 | 2367 |  |  | 2367
CO#2 New Sinks (Replace Hot Sinks) | 2020-06-10 | 12309 |  |  | 12309
CO#3 CR Closets Ref 10,11,12,14,15,16,17,18 | 2020-06-10 | 15320 |  | 15320
CO#4 Rev 2 L4 WC's & Admin Office - | 2020-07-08 | 11280 |  | 11280
CO#5 L1 L4 Admin Sinks & Lib Electrical | 2020-07-08 | 4016 |  |  | 4016
CO#6 R1 Wire Parking Lot Lighting | 2020-06-24 | 5400 |  |  | 5400
CO#7 Install Admin Office HVAC (Scott) | 2020-07-08 | 17150 |  |  | 17150
CO#8 Miscellaneous Electric & Plumbing | 2020-07-08 | 1094 |  |  | 1094
CO#9 Electrical & Data Installs (Sarracco) | Not Approved | 0 | [8 empty] | Use R&B and Go to BOS for contrract
CO10R1 Install Washer/Dryer in L4-L5 | 2020-07-22 | 1493 |  |  | 1493
CO#11 Credit for 1 cabinet in Ref 24 | 2020-07-22 | -1241 |  |  | -1241
CO#12 Circulation Desk Back Wall | 2020-07-22 | 5663 |  |  | 5663
CO#13 MEP Duct Repair + New Sink/Admin | 2020-08-11 | 2288 |  |  | 2288
CO#14 Power Pole & Outlets Media Ct | 2020-08-26 | 994 |  |  | 994
CO#16 Reconnect Heaters left by Bestec | 2020-09-08 | 1094 |  |  | 1094
CO#17 Rewire Admin Office + Security | 2020-09-08 | 1219 |  |  | 1219
CO#15 Art Room Outlets, Admin Finishes | 2020-09-23 | 3305 |  |  | 3305
CO#18 Repair Air Handler Admin Area | 2020-10-29 | 3701 |  |  | 3701
| 87452 | 87452
Catalyst
CO#1 Catalyst Additional Painting | 2020-06-10 | 34687.6 | 34687.6
CO#2 Additional Painting | 2020-06-10 | 43002.18 | 43002.18
CO#3 Catalyst Canvas Awning Replacement | 2020-07-08 | 4867.95 | 4867.95
CO#4 Patch Ceiling Tiles around new walls | 2020-07-08 | 1612.88 | 1612.88
CO#5 Café Base Cove | 2020-07-22 | 313.19 | 313.19
CO#6 Paint Punch List (see CO Folder) | 2020-08-26 | 7888.43 | 7888.43
CO#7 Paint Facaulty Lounge Walls | 2020-08-14 | 1660.97 | 1660.97
CO#8 Paint Facualty Louge Cabinets | NOT Approved | 0
CO#9 R1 Locker Room Storage Demolition | NOT Approved | 0 | 0 | [7 empty] | Not to Exceed !0,000 /Fire Marshell Issue on 8/26
CO#10 Paint Media Center (Entire) | 2020-08-26 | 844.56 | 844.56
CO#1 Concrete Repair Bus Canapy | 2020-09-09 | 2932.5 | 2932.5
| 140079.32 | 97810.26
.
Furniture Vendors
Furniture Art Room (Ref# L6) Worthington | 2020-06-24 | 6011.63 |  |  |  |  | 6011.63 |  |  |  | $,9,510.23 -2,7799.60-719.00 Renzoni to get PO (see Email)
Furniture Personalized (Ref# 6) Signature | 2020-06-24 | 8048.65 |  |  |  |  | 8048.65 |  |  |  | Delayed due COVID Concerns
14060.28
S&S
CO#1 Light Bases, Polls/Conduit Trenching | 2020-06-24 | 4796 | [6 empty] | 4796
CO#2 Catch Basin (not on plan) | 2020-06-24 | 4500 | [6 empty] | 4500
CO#3 Additional Rock @$300 py (170cy-50cy) |  | 31500 | [6 empty] | 31500
| 40796 | 40796
B&B Engineering
Civil - Parking Lot Site Plan | 2020-07-22 | 4478.63 | [5 empty] | 4478.63
4478.63
TECTON
Way Finding Signage - Design | 2020-06-10 | 3320 | [5 empty] | 3320
3320
Laurentano - Signage
Way Finding Signage -Install |  | 9856.06 | [5 empty] | 9856.06
9856.06
BESTEC | 2020-06-10 | 0
Additional Mitigation - Bestec |  | 41322.68 |  |  |  | 41322.68
Inv 58789 |  | 8677.32 |  |  |  | 8677.32
Red 24 - 4 Points |  | 0
Red 19-20 - 4 Points |  | 0
Red 9 - 4 Points |  | 0
Red 5 - 4 Points & Floor |  | 0
Ref 6 - Floor |  | 0
Sink Disposal (23 sinks) |  | 0
50000
Reimbrusements
Rich Krueger - 24x36 Printing | 2020-08-02 | 170.7 |  |  |  | 170.7
Herman Schuler - Smartsheet License | 2020-08-02 | 158.21 |  |  |  | 158.21 |  |  |  |  | Paid
328.91
Miscellaneous
BCI CO#200631 Berber Walkoff Mats | 2020-07-22 | 1800 |  |  |  |  | 1800 |  |  |  | Bartholomew Contract Interiors
BCI CO#200608Floor Patching 200 sf | 2020-07-22 | 1774.97 |  |  |  |  | 1774.97 |  |  |  | Bartholomew Contract Interiors
Move the Shed |  | 1900 |  |  |  |  | 1900 |  |  |  | Pending receipt of Quote from Georve Renzoni
5474.97
RnB (Pending BOS Approval of Contract}
20944 Move from OCS to GOMS (Not Valid) | 2020-06-24 | 0 |  |  | 0 | [5 empty] | Received 6/24 IS THIS VALID
20992 7/7/2020 Move 6 boards from OCS to GOMS | 2020-08-11 | 7717.66 |  |  | 7717.66 | [5 empty] | Received 8/11
20949 6/24/2020 GOMS Takedown smartboards | 2020-08-11 | 1172 |  |  | 1172 | [5 empty] | Received 8/11
21017 7/15/2020 Power Extensions | 2020-08-11 | 6490 |  |  | 6490 | [5 empty] | Received 8/11
Preferred Electric Invoice 17766 | 2020-09-23 | 3869 |  |  | 3869 | [5 empty] | To be allocated to admin Stuff
19248.66
Gym Audio & Lighting | 2020-07-22 | [9 empty] | Cancelled by BOE Due Covid Concerns
Audio |  | 0 | [8 empty] | 12,318.22 Discuss at 7/22 Meeting with Rob
Lighting |  | 0 | [8 empty] | 15,544.65 Discuss at 7/22 Meeting with Rob
|  | 0 | [8 empty] | 27862.87
|  | 8-1 | [8 empty] | 37808.76
** Total |  | 344825.77 | 97810.26 | 26600 | 80100.66 | 50328.91 | 31535.25 | 17654.69 | 40796 | 0
Total Change Orders |  | 344825.77
Total Awarded Contracts |  | 998728.6
Total Approved Budget/Awarded Budget | 1409226 | 1343554.37
Contingency Remaining |  | 65671.63

## Catalyst Contract
Catalyst Contract
Invoice# | Inv Date | Amount | Approval date | Invoices
Contract | 2020-05-20 | 149816
Inv #1 | 2020-06-08 |  | 2020-06-10 | -46695.5
CO#1 | 2020-06-10 | 34687.6 | 2020-06-10 |  |  | Painting
CO#2 | 2020-06-10 | 43002.18 | 2020-06-10 |  |  | Additional Painting (part of $80,000 motion)
CO#3 | 2020-07-08 | 4867.95 | 2020-07-08 |  |  | Green Awning Replacement
CO#4 | 2020-07-08 | 1612.88 | 2020-07-08 |  |  | Ceiling Tile Replacemnent Around New Walls
Inv#2 | 2020-07-08 |  | 2020-06-24 | -63252.4
CO#5 | 2020-07-22 | 313.19 | 2020-07-22 |  |  | Cafeteria Cove Molding
Inv#3 | 1905-07-12 |  | 2020-08-12 | -82898.07
CO#6 | 2020-08-07 | 7888.43 | 2020-08-12 |  |  | Painting Punchlist (see CO Folder for details
CO#7 | 2020-08-12 | 1660.97 | 2020-08-12 |  |  | Paint Walls in Faculty Louge CMU
CO#8 | 2020-08-19 |  |  |  |  | Paint Cabinets in CMU ( Not Approved)
CO#9 R1 | 2020-08-17 | 42269.06 |  |  |  | Demolish Locker Room - Remove partial walls FC Compliance
CO#10 | 2020-08-21 | 844.56 |  |  |  | Paint Media Center
CO#11 | 2020-09-08 | 2932.5 |  |  |  | Additional Concrete Patching to Weatherproof Bua Canopy
Inv #4 | 2020-09-23 |  |  | -54790.03
Over+/Under- |  | 289895.32 |  | -247636 | 42259.32
*Total CO's* |  | 140079.32
SIFCO Inc. John Sayadoff
Off 860 688-3331 Office 860 874-9878 Cell Jsayadoff@sifcoinc.net
Ben Moore Paint
Lower Hallway walls/Gym & Café |  |  | Blue 785
Admin Office Floor to Ceiling |  |  | Half Strength Blue 785
Upper Hallway walls |  |  | Cloud 9 OC-119
Inside Office Trim |  |  | Cloud 9 OC-119
Classroom Doors & Frames |  |  | Blue AF-530
Stairwell Risers & Railing |  |  | Blue AF-530
Classroom Wall & upper Gym |  |  | Match current wall color
Chromacolor |  |  | Ref#6 Video Wall
Bus Canopy Posts
Bus Canopy Facia
Bus Canopy Underside
Bus Canapy Roof
Victoria Blue 70.8 in 502V2-50677C |  |  | Admin Entrance Awning |  |  |  | From Soltis 502 Catalog Stored in Catayst Change Order Folder

## Legacy Contract
Legacy Contract
Invoice# | Inv Date | Amount | Approval date | Retainage | Invoices | Total+Retain
Contract |  | 378413 | 2020-05-20
CO#1 | 2020-06-05 | 2367 | 2020-06-10 |  |  |  | Plumbing V | aslue Replacement | CO#1
CO#2 | 2020-06-08 | 12309 | 2020-06-10 |  |  |  | Replace Asbestos "Hot" Sinks |  | CO#2
CO#3 | 2020-06-08 | 15320 | 2020-06-10 |  |  |  | Replace Closet Cabinets (Mitigation Classeooms |  | CO#3
CO#4 R2 | 2020-07-08 | 11280 | 2020-07-08 |  |  |  | Ref#L4 Add 2 WD & Admin Remove Sink Book Shelves
L20025-01 | 2020-05-22 |  | 2020-05-27 | -1892 | -35950
CO#5 | 2020-07-08 | 4016 | 2020-07-08 |  |  |  | Remove 8' of heating on 2 side walls L1,L4 Admin Plumbing
CO#6 R1 |  | 5400 | 2020-06-24 |  |  |  | Wire Parking Lot Lighting
CO#7 | 2020-07-08 | 17150 | 2020-07-08 |  |  |  | Admin Office HVAC
L20025-02 | 2020-06-24 |  | 2020-06-24 | -6610 | -89631
CO#8 | 2020-07-08 | 1094 | 2020-07-08 |  |  |  | Misc Plumbing & Electrical
CO#9 | NOT Apprv. | [5 empty] | Wiring for Desks and Smartboards (Denied - BOE is doing)
CO#10R1 |  | 1493 | 2020-07-22 |  |  |  | Install Washer/Dryer in L5
CO#11 | 2020-07-09 | -1241 | 2020-07-22 |  |  |  | Credit for cabinet in Ref#24
CO#12 | 2020-07-16 | 5663 | 2020-07-22 |  |  |  | Ref#9 Circulation Desk Rear Wall
L20025-03 | 2020-07-22 |  | 2020-07-22 | -21313 | -279370
CO#13 | 2020-08-12 | 2288 | 2020-08-12 |  |  |  | Admin Sink, HVAC Duck repair
CO#14 | 2020-08-21 | 994 |  |  |  |  | New Desk Wiring
L20025-04R1 | 2020-08-25 |  | 2020-08-26 | -22827 | -28769
CO#16 | 2020-09-09 | 1094 | 2020-09-09 |  |  |  | Reconnect Electric Heaters disconnected by Bestec
CO#17 | 2020-09-09 | 1219 | 2020-09-09 |  |  |  | Rewire Admin Office outlets and Security
CO#15 | 2020-09-23 | 3305 | 2020-09-23 |  |  |  | Art Room Outlets - Admin Finishes
L20025-05 | 2020-09-23 |  |  | -23108 | -5337
L20025-06 | 2020-08-26 |  |  |  | -23108 |  | Reimbruse Retainage
CO#18 | 2020-10-29 | 3701 | TBA |  |  |  | Air Handler Moter Replacement
L20023-07 | 2020-11-25 |  | TBA |  | -3701
Over+/Under- |  | 465865 |  | 0 | -465866 | -465866 |  | -1
Retainage | 2020-08-26 | [5 empty] | Release of Retainage - authorized 8/26/2020
*Total CO's* |  | 87452 |  |  | -465866
Contract |  | -378414
465865
-1

## Priemier Contract
Premier Contract - Playscape
Invoice# | Inv Date | Amount | Approval date | Invoices
Contract |  | 74862 | 2020-06-24 |  | BOE 7/13/2020 | BOS 7/23/2020
Over+/Under- |  | 74862 |  | 0 | 74862
Component Colors |  | Colors (from Catalog)
Aluminum/Steel
Vertical Posts |  | 8
Horizontal Rails |  | 21
Molded Polyethylene |  | 19
Polyenthlene Panels (Two Tone) |  | 21
See Catalog Files in Final Contract Folder

## S&S Contract
S&S Contract
Invoice# | Inv Date | Amount | Approval date | Invoices
Contract | `5/20/2020 | 306700 | 2020-05-20
CO#1 | 2020-06-22 | 4796 | 2020-06-24 |  | Two Light Bases & Poles
CO#2 | 2020-06-22 | 4500 | 2020-06-24 |  | Catch Basin not on plan
CO#3 | 2020-08-12 | 31500 |  |  | Additional Rock Hammering & Removal
1648189 | 2020-08-27 |  |  | -347496
Over+/Under- |  | 347496 |  | -347496 | 0
*Total CO's* |  | 40796
Basketball Hoop Height 8' 6"

## StageRight Contract
StageRight Contract
Invoice# | Inv Date | Amount | Approval date | Invoice | PO#
Contract | 2020-05-20 | 63800 | 2020-05-20 |  | PO#26432 | 2020-06-25 | Via Email to Jim Johnson
272388 | 2020-08-18 |  |  | -63800 | Sent to Jim Hliva for Payment (see email)
Over+/Under- |  | 63800 |  | -63800 | 0

## Tecton Contract
Tecton Contract
Invoice# | Inv Date | Amount | Approval date
Contract | 2019-07-15 | -9900
42423 | 2019-10-31 | 6061.25 | 2020-11-13 |  | paid
42554 | 2019-11-30 | 880 | 2020-02-27 |  | paid
42645 | 2020-01-31 | 960 | 2020-02-27 |  | paid
42752 | 2020-02-29 | 1598.75 | 2020-04-22 |  | paid
42913 | 2020-04-30 | 2400 | 2020-05-13 |  | Agenda
43092 | 2020-06-30 | 640 |  | -640 | 2020-09-09
Over+/Under- |  | 2640 |  |  | Posted to Project Control
New Contract |  | 3320 | 2020-06-10 |  | Wayfinding Signage
43091 |  |  | 2020-09-09 | -3240
Over/Under |  | 3320 |  | -3240

## Furniture,Signage & Misc
Signature Products Personalized Learning Center Furniturre
Invoice# | Inv Date | Amount | Approval date |  | PO #
Contract |  | 8048.65 |  |  | Renonzi Responsible for PO Request
Over+/Under- |  | 8048.65
Worthington Direct Art Room Ref# L6 Personalized Learning Center Furniturre
| Inv Date | Amount | Approval date |  | PO #
Contract |  | 6011.63 | 2020-06-24 |  | Reduced from Or3iginal Quote by the cost of tables
Renonzi Responsible for PO Request
Over+/Under- |  | 6011.63
R&B Move Smartboards
| Inv Date | Amount | Approval date | Invoice
Contract |  |  | 2020-06-24 |  | Not to exceed $20,000 - Pending Contract
Quote 20944 | 2020-06-24 | 0 |  |  | 20944 Move from OCS to GOMS (Not Valid)
Quote 20992 | 2020-08-11 | 7717.66 |  |  | 20992 7/7/2020 Move 6 boards from OCS to GOMS
Quote 20949 | 2020-08-11 | 1172 |  |  | 20949 6/24/2020 GOMS Takedown smartboards
Quote 20949 | 2020-08-11 | 6490 |  |  | 21017 7/15/2020 Power Extensions
Not to exceed $20,000 | 2020-07-08 | 3869 |  |  | Not to exceed $20,000 - Pending Contract
Invoice 59364 | 2020-08-21 |  |  | -7717.66
Invoice 59364 | 2020-08-21 |  |  | -1172
Invoice 59366 | 2020-08-21 |  |  | -6490
Invoice 17766 | 2020-09-23 |  |  | -3869
Over+/Under- |  | 19248.66 |  | -19248.66 | 0
B & B Engineering GOMS Repaving Site Plan
2020-03-01 |  | 4478.63 | 2020-07-22
991-50 | 2020-07-01 |  | 2020-08-18 | -4478.63
Over+/Under- |  | 4478.63 |  | -4478.63 | 0
Flooring Contract Miscellaneous Floor Patch Repair
2020-07-22 | 200608 | 1774.97 | 2020-07-22
2020-07-22 | 200631 | 1800 | 2020-07-22
2020-08-21 | 59036 |  | 2020-08-26 | -1774.97 |  | sent for payment 11/12/2020 (my ommission)
2020-08-31 | 59083 |  | 2020-08-26 | -1800
Over+/Under- |  | 3574.97 |  | -3574.97 | 0
Fire Alarm Sytem Reprogram Panel & System for New Room Numbers
|  | 600 | 2020-07-22
Over+/Under- |  | 600
USA Waste Management Dumsters
2020-06-05 | 602507778 | 3667.1
2020-06-12 | 602510494 | 1782.8
2020-06-19 | 602511804 | 1437.5
2020-07-24 | 602533786 | 528.35
2020-07-31 | 602536349 | 50
2020-08-12 | 602507778 |  | -3667.1
2020-08-12 | 602510494 |  | -1782.8
2020-08-12 | 602511804 |  | -1437.5
2020-08-12 | 602533786 |  | -528.35
2020-08-12 | 602536349 |  | -50
2020-08-07 | 602539701 | 70
2020-08-14 | 602541816 | 70
2020-08-21 | 602548447 | 70
2020-09-09 | 602539701 |  | -70
2020-09-09 | 602541816 |  | -70
2020-09-09 | 602548447 |  | -70
2020-08-31 | 602550807 | 615.85
2020-09-23 |  |  | -615.85
Over+/Under- |  | 8291.6 | -8291.6 |  | 0
Lauretano Sign Group Dumsters
2020-08-11 | Quote 39111 | 9856.06
Over+/Under- |  | 9856.06 | 0 |  | 9856.06
Over+/Under- |  | 19712.12
Meyers Moving Dumsters
2020-04-07 | Letter in file | 12306 |  |  | Approved
2020-05-21 | 120-014250 |  | -3575.5 |  | 2020-08-12
2020-07-27 | 120-014957 |  | 0 |  | 2020-09-09 | BOE Exp | -12123
2020-08-31 | 120-015695 |  | 0 |  | 2020-09-09 | BOE Exp | -27329
2020-09-15 | 120-016007 |  | -8730.5
Over+/Under- |  | 12306 | -12306 |  | 0
Walshs Country Store Dumsters
2020-09-23 | Qoute | 1900
2020-10-05 | Invoice |  | -1900
|  | 1900 | -1900 | 0
Asbestos Mitigation
| Qoute | 50000
2020-10-05 | Inv 58789 |  | -8677.32 |  | BCI FLOORING
|  | 50000 | -8677.32 | 41322.68

## Catayst CO#1 Paint
CO 1 Catalyst Painting
1st floor doors & frames admin & gym corridor | 5940
paint admin area doors & frames | 1800
Paint Classroom walls at milwork replacement area | 4800
Paint stairwell railings risers & stringers | 3120
Paint lower level doors & Frames | 5400
Paint Café Doors & Frames | 2520
Paint Gym walls upper cover murals | 3120
Paint Gym Doors & Frames | 2880
** Total Cost ** | 29580
Insurance & Profit | 5117.34
*** Net Cost *** | 34697.34
CO #2 Remaining GOMS Painting
First Floor Corridor Walls - Two Tone | 9360
Paint Admin Area Walls First Floor | 4680
Paint Stairwell Walls to cover Murals | 3120
Paint Lower Level Walls - Two Tone | 12480
Paint Cafe Lower Walls | 3900
Paint Gym Lower Walls | 3120
** Total Cost ** | 36660
Insurance & Profit | 6342.18
*** Net Cost *** | 43002.18