## O&G Itemized
Description |  | Amount | Sub-Total | Winning Bid | Varance | Status | Due Date | Bidder | Bid $ | Bidder | Bid $ | Bidder | Bid $ | Bidder | Bid $ | Bidder | Bid $
1.00 General Conditions
| Movers | 0 |  | 61607 |  | Requirements
| Dumpsters | 0 |  | 10000 |  | Requirements
| Tecton RFP Support | 0 |  | 2000
| Asbestos Mitigation/Air Qual/Flooring | 164534
| **Total** |  | 164534 | 73607 | 90927
1.01 Asbestos Abatement
| Asbetos Mitigation | 150000 |  | 0 |  | GR
| Air Quality Testing |  |  |  |  | GR
| New Flooring |  |  |  |  | GR
| **Total** |  | 150000 | 0 | 150000
1.02 One-to-One Millwork Replacement | [5 empty] | OPS2020-04 | 2020-03-27
| Demo Base Cabinets (29 Areas) L22' x29' Ea) | 9528 |  |  |  | OPS2020-04
| Demo Upper Cabinets (29 Areas) L22' x29' Ea) | 9528 |  |  |  | OPS2020-04
| Wood Base Cabinets | 129514 |  |  |  | OPS2020-04
| Media CenterFurniture Improvments | 20000 |  |  |  | Requirements
| Wood Wall Cabinets | 123134 |  |  |  | OPS2020-04
| Countertops - Formica | 80974 |  | 378413 |  | OPS2020-04 |  | Legacy GC BID | 378413
1.06 Art Room Improvements | [5 empty] | OPS2020-04 | 2020-03-27 | Approved 5/6 BOS
| Demo Base Cabinets | 3870 |  |  |  | OPS2020-04
| Demo Upper Cabinets | 3650 |  |  |  | OPS2020-04
| Cabinet - Base Level Plam - Base Cabinet W/Sink | 960 |  |  |  | OPS2020-04
| Cabinet - Base Level Plam - Wall Cabinet | 1000 |  |  |  | OPS2020-04
| Countertops - Formica w/Wood Edge | 2792 |  |  |  | OPS2020-04
| Furniture Improvements (AIA Allow) | 2000 |  |  |  | OPS2020-04
| 3 New Sinks + U/G Drain to Bathroom | 5000 |  |  |  | OPS2020-04
| Cut & Patch Floor for Drain Line | 3000 |  |  |  | OPS2020-05 | 2020-04-10
| **Total** |  | 394950 | 378413 | 16537
1.03 Select Ceiling Tile Replacement
| Remove Ceiling Tile and Grid | 0 |  |  |  | Requirements
| Ceiling Plain Tile | 5000 |  |  |  | Requirements
| **Total** |  | 5000 | 0 | 5000
1.04 Wayfinding / Signage Throughout | [5 empty] | Requirements
| Remove Wayfinding Signs | 5161 |  |  |  | Requirements
| Remove Room Signs | 5075 |  |  |  | Requirements
| Sign - Room Id | 11320 |  |  |  | Requirements
| Sign - Exit | 6330 |  |  |  | Requirements
| **Total** |  | 27886 | 0 | 27886
1.05 Science Labs (2 loc) Furniture Replacement
| Lab Furniture | 20000 |  |  |  | Requirements
| **Total** |  | 20000 | 0 | 20000 | Requirements
1.07 Gymnasium Improvements
| Refurbish Existing Gym Divider | 27210 |  |  |  | Requirements
| Acoustical Wall Panels 8' High @ 2 Long Walls | 20160 |  |  |  | Requirements
| Raised Portable Platform W/Accessibility PO26432 | 58000 |  | 63800 |  | OPS2020-02 | 2020-03-05 | StageRight | 63800 | SICO | 69,000 24" no ramp or stage surround
Delete Gym Divider Curtain (Refurbish Existing)
| A/V Infrastructure(Relocate Existing Equipment, Power) | 8000 |  |  |  | Requirements | 2020-04-10
| **Total** |  | 113370 | 63800 | 49570
1.08 Literacy Center Furniture Improvement
| Furniture Improvements | 20000 |  |  |  | Requirements
| Demo Wall & Rebuild |  |  |  |  | OPS2020-05 | 2020-04-10
1.09 Personalized Learning Center
| Demo Temp Partician L22' x H' | 741 |  |  |  | OPS2020-05 | 2020-04-10
| Paint & Touchup (estim) | 500 |  |  |  | OPS2020-05 | 2020-04-10
1.10 Media Center
| Demo Temp Partician (2Walls) L22 x H9' @ 2 Ea | 1480 |  |  |  | OPS2020-05 | 2020-04-10
| Paint Touch-Up (estimate) | 500 |  |  |  | OPS2020-05 | 2020-04-10
1.11 Ref #12 Demo & Rebuild 2 Walls | [5 empty] | OPS2020-05 | 2020-04-10
1.12 Ref #19-20 Demo 3 Walls, Rebuild 2 Walls | [5 empty] | OPS2020-05 | 2020-04-10
1.13 Ref # 24 - Demo 2 Walls & Rebuild 2 Walls | [5 empty] | OPS2020-05 | 2020-04-10
1.14 Ref # L4-L5 New Music Room - Demo 1 Wall |  |  |  | 149816 |  |  |  | Catalyst | 149816 | 5-7-2020 Including GYM & Bus Canopy
| **Total** |  | 23221 | 149816 | -126595 |  |  | Tabled 5/6
1.15 Exterior Improvements
| Clean Exterior Building, Exterior Paint, Caulk (no plans - AIA) | 7500 |  |  |  | OPS2020-05 | 2020-04-10
| Site Prep & Playground (no Plans - AIA) | 150000 |  |  |  | OPS2020-06 | 2020-04-10 | Premier | 46460
| Pave & Restripe Parking Lot (no Plans - AIA allow) | 100000 |  | 306700 |  | OPS2020-07 | 2020-04-10 | Marini | 302900 | S&S | 306700 | Guarrarra | 354000 | All American | 371210 | earthworks | 396228
| **Total** |  | 257500 | 306700 | -49200 |  |  | S&S Awarded |  | Awarded 3/6
| Project Financial Status | 1156461 | 1156461 | 972336 | 184125
| Tecton Estimate | 1032400 | [6 empty] | 68310 |  | 64510 |  | 17210
| Professional Fees | 77430 | 77430
| Design Contingency | 103240 | 103240
| Escalation | 25810 | 25810
| Liabability Insuance | 15486 | 15486
| Contractor Overhead & Profit | 103240 | 103240
| Buiding Permit | 0 | 0
| Owner"s Contingency | 51620 | 51620
|  | 376826 | 376826
| Summary - Approved/O&G Estimates | 1409226 | 1533287 | -124061
| Reconciliation Approved/O&G/Budget |  | 1409226 | 436890

## Change Orders
Change Orders
Description | Approved | Catalyst | Legacy | Saracco | Bestec | GR & Sean | Tecton | Premier | S&S | Misc.
COVID Reserve Clean Building | [9 empty] | 15000
Legacy
CO#1 Replace Shutoff Valves | 2020-06-10 |  |  | 2367
CO#2 New Sinks (Replace Hot Sinks) | 2020-06-10 |  |  | 12309
CO#3 CR Closets Ref 10,11,12,14,15,16,17,18 | 2020-06-10 |  | 15320
CO#4 Rev 2 L4 WC's & Admin Office - | 2020-07-08 |  | 11280
CO#5 L1 L4 Sinks & Electrical | 2020-07-08 |  |  | 4016
CO#6 R1 Wire Parking Lot Lighting | 2020-06-24 |  |  | 5400
CO#7 Install Admin Office HVAC (Scott) | 2020-07-08 |  |  | 17150
CO#9 Electrical & Data Installs (Sarracco) |  |  |  | 14843
Premiere
Playscape - Purchase and Install | 2020-06-24 | [6 empty] | 74862
Catalyst
CO#1 Catalyst Additional Painting | 2020-06-10 | 34687.6
CO#2 Additional Painting | 2020-06-10 | 43002.18
CO#2 Catalyst Canvas Awning Replacement |  | 6000
Furniture Vendors
Furniture Art Room (Ref# L6) Worthington | 2020-06-24 | [8 empty] | 9510.23 | Renzoni to get PO (see Email)
Furniture Personalized (Ref# 6) Signature | 2020-06-24 | [8 empty] | 8048.65 | Renzoni to get PO (see Email)
S&S
CO#1 Light Bases, Polls/Conduit Trenching | 2020-06-24 | [7 empty] | 4796
CO#2 Catch Basin (not on plan) | 2020-06-24 | [7 empty] | 4500
CO#3 Additional Rock @$300 py (170cy-50cy) | [8 empty] | 36000
TECTON
Way Finding Signage - Design | 2020-06-10 | [5 empty] | 3320
Way Finding Signage -Install | [6 empty] | 9350
BESTEC | 2020-06-10 |  |  |  | 50000
Additional Mitigation - Bestec
Red 12 - 4 Points
Red 24 - 4 Points
Red 19-20 - 4 Points
Red 9 - 4 Points
Red 5 - 4 Points & Floor
Ref 6 - Floor
Sink Disposal (23 sinks)
Window Security (Declined by town)
Furniture Disposal
Move & Install 10 OCS Smartboards | [5 empty] | 11348.78
Gym Audio & Lighting
Audio | [9 empty] | 12318.22 | Need to Review
Lighting | [9 empty] | 15544.65 | Need to Review
** Total |  | 83689.78 | 26600 | 56085 | 50000 | 11348.78 | 12670 | 74862 | 45296 | 60421.75
*** Change Order Grand Total/Max Range |  | 420973.31
From Itemized to Date |  | 436890
Remaining Budget |  | 15916.69

## Catalyst Contract
Catalyst Contract
Invoice# | Inv Date | Amount | Approval date
Contract | 2020-05-20 | 149816
Inv #1 | 2020-06-08 | -46695.5 | 2020-06-10
CO#1 | 2020-06-10 | 34687.6 |  | Painting
CO#2 | 2020-06-10 | 43002.18 | 2020-06-10 | Additional Painting (part of $80,000 motion)
CO#3 |  | 6000 |  | Green Awning Replacement
Over+/Under- |  | 186810.28
*Total CO's* |  | 83689.78
SIFCO Inc. John Sayadoff
Off 860 688-3331 Office 860 874-9878 Cell Jsayadoff@sifcoinc.net
Ben Moore Paint
Lower Hallway walls/Gym & Café |  |  | Blue 785
Admin Office Floor to Ceiling |  |  | Half Strength Blue 785
Upper Hallway walls |  |  | Cloud 9 OC-119
Inside Office Trim |  |  | Cloud 9 OC-119
Classroom Doors & Frames |  |  | Blue AF-530
Stairwell Risers & Railing |  |  | Blue AF-530
Classroom Wall & upper Gym |  |  | Match current wall color

## Legacy Contract
Legacy Contract | [6 empty] | as of L20025-02
Invoice# | Inv Date | Amount | Approval date | Retainage |  |  | 2020-06-24
Contract |  | 378413 | 2020-05-20 |  |  |  | 378413
CO#1 | 2020-06-05 | 2367 | 2020-06-10 |  | Plumbing | CO#1 | 2367
CO#2 | 2020-06-08 | 12309 | 2020-06-10 |  | Replace "Hot" Sinks | CO#2 | 12309
CO#3 | 2020-06-08 | 15320 | 2020-06-10 |  | Replace Closet Cabinets | CO#3 | 15320
CO#4 R2 | 2020-06-18 | 11280 |  |  | Ref#4 Add 2 WD & Sink
L20025-01 | 2020-05-22 | -35950 | 2020-05-27 | 1892 |  |  | -35950
CO#5 |  | 4016 |  |  | Remove 8 feet of heating on 2 side walls + Admin Plumbing
CO#6 R1 |  | 5400 | 2020-06-24 |  | Wire Parking Lot Lighting
CO#7 |  | 17150 |  |  | Admin Office HVAC
L20025-02 | 2020-06-24 | -89631 | 2020-06-24 | 6610 |  |  | -89631
CO#9 |  | 14843 |  |  | Classroom Wiring & Data
Over+/Under- |  | 335517 |  |  |  |  | 282828
*Total CO's* |  | 82685

## S&S Contract
S&S Contract
Invoice# | Inv Date | Amount | Approval date
Contract | `5/20/2020 | 306700 | 2020-05-20
CO#1 | 2020-06-22 | 4796 | 2020-06-24 | Two Light Bases & Poles
CO#2 | 2020-06-22 | 4500 | 2020-06-24 | Catch Basin not on plan
CO#3 |  |  |  | Additional Rock
Over+/Under- |  | 315996
*Total CO's* |  | 9296
Basketball Hoop Height 8' 6"

## Priemier Contract
Premier Contract
Invoice# | Inv Date | Amount | Approval date
Contract |  | 74862
Over+/Under- |  | 74862
Compnent Colors |  | Colors (from Catalog)
Aluminum/Steel
Vertical Posts |  | 8
Horizontal Rails |  | 21
Molded Polyethylene |  | 19
Polyenthlene Panels (Two Tone) |  | 21
See Catalog Files in Final Contract Folder

## StageRight Contract
StageRight Contract
Invoice# | Inv Date | Amount | Approval date | PO#
Contract | 2020-05-20 | 63800 | 2020-05-20 | PO#26432 | 2020-06-25 | Via Email to Jim Johnson
Over+/Under- |  | 63800

## Tecton Contract
Tecton Contract
Invoice# | Inv Date | Amount | Approval date
Contract | 2019-07-15 | -9900
42423 | 2019-10-31 | 6061.25 | 2020-11-13 | paid
42554 | 2019-11-30 | 880 | 2020-02-27 | paid
42645 | 2020-01-31 | 960 | 2020-02-27 | paid
42752 | 2020-02-29 | 1598.75 | 2020-04-22 | paid
42913 | 2020-04-30 | 2400 | 2020-05-13 | Agenda
Over+/Under- |  | 2000 |  | Posted to Project Control
New Contract |  | 3320 | 2020-06-10 | Wayfinding Signage

## Furniture Misc
Signature Products Personalized Learning Center Furniturre
Invoice# | Inv Date | Amount | Approval date | PO #
Contract |  | 8048.65
Over+/Under- |  | 8048.65
Worthington Direct Art Room Ref# L6 Personalized Learning Center Furniturre
| Inv Date | Amount | Approval date | PO #
Contract |  | 9510.23 | 2020-06-24
Over+/Under- |  | 9510.23
R&B Move 11 Smartboards
| Inv Date | Amount | Approval date
Contract |  | 11348.78 | 2020-06-24
Over+/Under- |  | 11348.78

## Reconcile Project Control
Great Oak Middle Schoool Evaluation & Improvements (TA: OXF02AR)
Project Tracking
Proposed Project Cost Summary - 8/14/2019 approved BOS, BOF, TM
Work to be Completed by August 2020
| Total Gross Area: | 73000 | Tecton Cost Estimate |  | O&G Estimates (See Sheet2)
Scope of Work |  |  | LS | Subtotal | Cost Estimate | Var -TT-OG
1.00 General Conditions |  |  |  |  | 164534 | -164534
1.01 Asbestos Abatement |  |  | 300000 | 300000 | 150000 | 150000
1.02 One-to-One Millwork Replacement |  |  |  | 104400 | 394950 | -290550
1.03 Select Ceiling Tile Replacement |  |  | 50000 | 50000 | 5000 | 45000
1.04 Wayfinding / Signage Throughout |  |  | 50000 | 50000 | 27886 | 22114
1.05 Science Labs (2 loc) Furniture Replacement |  |  |  | 40000 | 20000 | 20000
1.06 Art Room Improvements |  |  |  | 38000 | 0 | 38000
Provide Built-In Perimeter Shelving w/Sink |  |  | 18000
Furniture Improvements |  |  | 20000
1.07 Gymnasium Improvements |  |  |  | 75000 | 113370 | -38370
Raised Platform w/Accessibility (24' X 40') |  |  | 32000
Room Divider Curtain |  |  | 15000
A/V Infrastructure (Relocate Existing Equipment, Provide Power) |  |  | 8000
Acoustic Wall Panels |  |  | 20000
1.08 Literacy Center Furniture Improvement |  |  | 20000 | 20000 | 23221 | -3221
1.10 Media Center |  |  |  | 28000 | 0 | 28000
Demolition of Temporary Partitions (2) |  |  | 8000
Furniture Improvements |  |  | 20000
1.09 Personalized Learning Center |  |  |  | 4000 | 0 | 4000
Demolition of Temporary Partition |  |  | 4000
1.15 Exterior Improvements |  |  |  | 323000 | 257500 | 65500
Site Prep & Playground |  |  | 150000
Exterior Paint, Caulk, Trim |  |  | 7500
Paving & Restriping of Parking Lot |  |  | 100000
Total |  |  |  | 1032400 | 1156461 | -124061 | 0 | 0
Professional Fees |  |  |  | 77430 |  | 77430 |  |  | Allocate
Design Contingency |  |  |  | 103240 |  | 103240 |  |  | Allocate
Escalation |  |  |  | 25810 |  | 25810 |  |  | Allocate
Liability Insurance (Builders Risk) |  |  |  | 15486 |  | 15486 |  |  | Allocate
Contractor Overhead & Profit |  |  |  | 103240 |  | 103240 |  |  | Allocate
Building Permit |  |  |  | 0 |  | 0 |  |  | Allocate
Owner's Contingency |  |  |  | 51620 |  | 51620 |  |  | Allocate
|  |  |  | 376826 |  | 376826
Total Project Cost /Contingency Balance |  |  |  | 1409226 | 1156461
[6 empty] | 1409226 |  | 252765

## Catayst CO#1 Paint
CO 1 Catalyst Painting
1st floor doors & frames admin & gym corridor | 5940
paint admin area doors & frames | 1800
Paint Classroom walls at milwork replacement area | 4800
Paint stairwell railings risers & stringers | 3120
Paint lower level doors & Frames | 5400
Paint Café Doors & Frames | 2520
Paint Gym walls upper cover murals | 3120
Paint Gym Doors & Frames | 2880
** Total Cost ** | 29580
Insurance & Profit | 5117.34
*** Net Cost *** | 34697.34
CO #2 Remaining GOMS Painting
First Floor Corridor Walls - Two Tone | 9360
Paint Admin Area Walls First Floor | 4680
Paint Stairwell Walls to cover Murals | 3120
Paint Lower Level Walls - Two Tone | 12480
Paint Cafe Lower Walls | 3900
Paint Gym Lower Walls | 3120
** Total Cost ** | 36660
Insurance & Profit | 6342.18
*** Net Cost *** | 43002.18